ExamVault — Daily Frontend + Backend Parallel Roadmap

React + TypeScript Frontend | ASP.NET Core .NET 8 Backend | Microservices | AI

# 1. Execution Rule

Every development day has BOTH frontend and backend work.

Do not spend an entire day only on React or only on .NET unless the other side is explicitly marked as verification/documentation.

Each day must finish with a working connection or verified contract between frontend and backend whenever the feature exists on both sides.

Phase 0 is still the starting point. No User Service business logic until the Phase 0 gate passes.

AI is designed early but implemented only at the AI milestone after Exam and Question foundations.

If either frontend or backend fails its daily gate, the day is not complete.

# 2. Target Folder Hierarchy

ExamVault
├── Frontend
│   └── ExamVault.Web                 ← React + TypeScript
│
├── Backend
│   ├── Gateway
│   │   └── OnlineExamSystem.ApiGateway
│   ├── Services
│   │   ├── UserService
│   │   ├── ExamService
│   │   ├── QuestionService
│   │   ├── SubmissionService
│   │   ├── ResultService
│   │   ├── NotificationService
│   │   └── AIService
│   └── Shared
│       ├── OnlineExamSystem.Shared.Contracts
│       ├── OnlineExamSystem.Shared.Events
│       └── OnlineExamSystem.Shared.Common
│
├── Tests
├── Docker
├── Documentation
├── ExamVault.sln
└── README.md

# 3. Daily Development Pattern

Every day follows this sequence:

1. Backend contract / API work
2. Frontend page/component work
3. Frontend API integration
4. Backend test
5. Frontend test
6. End-to-end verification
7. Git commit
8. Mark the day complete

React → Gateway → API → Application → Domain/Infrastructure → Database
React ← Gateway ← API ← Application ← Domain/Infrastructure ← Database

# PHASE 0 — FOUNDATION

## Day 1 — Phase 0: Repository + tooling

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create React/Vite project structure • Create base App.tsx/main.tsx • Create basic route placeholder | • Create ExamVault.sln and Backend folder • Create Gateway + User Service + Shared projects • Configure solution references |

Integration / Daily flow: Verify React starts and .NET solution restores.

Day complete when: React dev server + dotnet restore both succeed.

## Day 2 — Phase 0: Frontend/Backend skeleton

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create api, components, layouts, pages, routes, types, utils • Create shared frontend layout placeholder | • Create API/Application/Domain/Infrastructure folders/projects • Apply dependency rules |

Integration / Daily flow: No business API yet; verify folder boundaries.

Day complete when: No circular references; React and .NET are independent.

## Day 3 — Phase 0: Build and run

| Frontend — React | Backend — .NET |
| --- | --- |
| • Configure Vite, TypeScript, ESLint/Prettier • Create Home page | • Configure ASP.NET Core startup • Swagger/OpenAPI foundation • Development settings |

Integration / Daily flow: Run React and Gateway/User API independently.

Day complete when: npm run build + dotnet build pass.

## Day 4 — Phase 0: Configuration

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create frontend environment API-base-url configuration • Create basic Axios client | • Create appsettings.Development.json • Prepare User Secrets/environment-variable strategy |

Integration / Daily flow: Verify frontend can point to the backend URL without hardcoding it.

Day complete when: No secrets committed; configuration documented.

## Day 5 — Phase 0: Phase 0 gate

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create initial navigation shell • Add Login/Register placeholders | • Verify all projects build • Verify solution structure • Document startup commands |

Integration / Daily flow: Final Phase 0 end-to-end startup verification.

Day complete when: React + Gateway + User API start successfully; Phase 0 unlocked.

# PHASE 1 — USER SERVICE MVP

## Day 6 — Phase 1: User model foundation

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create Register page UI fields • Create API type/interface for Register request | • Create User entity • Create UserDbContext • Configure SQL Server |

Integration / Daily flow: Frontend form contract matches backend request DTO.

Day complete when: Backend builds and database connection is verified.

## Day 7 — Phase 1: Registration API

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create Register form validation • Loading/error/success states • Axios POST | • Create Register command/handler/validator • Password hashing • POST /api/users/register • Unit tests |

Integration / Daily flow: React Register → User API.

Day complete when: Successful user registration from React.

## Day 8 — Phase 1: Profile

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create Profile page • Create user model • Profile API hook | • Create GET /api/users/me foundation • Create DTO and handler • Tests |

Integration / Daily flow: React Profile consumes API response.

Day complete when: Profile data renders correctly.

## Day 9 — Phase 1: User gate

| Frontend — React | Backend — .NET |
| --- | --- |
| • Polish Register/Profile UI • Frontend validation tests | • API tests • Migration verification • Error handling review |

Integration / Daily flow: Full Register → API → DB → Profile flow.

Day complete when: User Service MVP works end-to-end.

# PHASE 2 — YARP API GATEWAY

## Day 10 — Phase 2: YARP foundation

| Frontend — React | Backend — .NET |
| --- | --- |
| • Configure Axios base URL for Gateway • Add Gateway-aware API client | • Install/configure YARP • Add User route and destination |

Integration / Daily flow: React points to Gateway instead of direct User API.

Day complete when: Register/Profile works through Gateway.

## Day 11 — Phase 2: Gateway integration

| Frontend — React | Backend — .NET |
| --- | --- |
| • Update all API calls to Gateway • Add API error interceptor | • Verify routing • Add health/connectivity checks • Document routes |

Integration / Daily flow: React → Gateway → User API.

Day complete when: No frontend direct calls to service URLs.

# PHASE 3 — JWT + REFRESH TOKEN

## Day 12 — Phase 3: Login UI + JWT backend

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create Login page • Form validation • Login API client | • JWT settings • Authentication middleware • Role claims |

Integration / Daily flow: Login request/response contract.

Day complete when: Login endpoint returns valid access token.

## Day 13 — Phase 3: Login integration

| Frontend — React | Backend — .NET |
| --- | --- |
| • Auth context/store • Save authentication state • Protected route foundation | • POST /api/users/login • Verify password • Generate access + refresh tokens |

Integration / Daily flow: React Login → Gateway → User API.

Day complete when: Admin/Student identity is available in React.

## Day 14 — Phase 3: Refresh + Logout

| Frontend — React | Backend — .NET |
| --- | --- |
| • Axios token handling • Refresh flow • Logout button | • Refresh endpoint • Token persistence/revocation • Logout endpoint |

Integration / Daily flow: Expired access token → refresh → retry request.

Day complete when: Refresh and logout work.

## Day 15 — Phase 3: Role-based UI

| Frontend — React | Backend — .NET |
| --- | --- |
| • AdminRoute • StudentRoute • Unauthorized page • Navigation by role | • Role authorization policies • Secure User endpoints |

Integration / Daily flow: Role from backend controls protected UI.

Day complete when: Protected routes and API authorization both work.

# PHASE 4 — MESSAGING

## Day 16 — Phase 4: Event contracts

| Frontend — React | Backend — .NET |
| --- | --- |
| • No major UI; add notification/status placeholder | • Create UserRegisteredEvent • Publisher abstraction • Shared event conventions |

Integration / Daily flow: Backend event contract prepared for UI-visible status later.

Day complete when: Event contract compiles.

## Day 17 — Phase 4: RabbitMQ local

| Frontend — React | Backend — .NET |
| --- | --- |
| • Add registration success message/status | • Publish UserRegisteredEvent • Create Notification consumer |

Integration / Daily flow: Register → event → consumer.

Day complete when: RabbitMQ event is received.

## Day 18 — Phase 4: Messaging hardening

| Frontend — React | Backend — .NET |
| --- | --- |
| • Show friendly async operation state where relevant | • Retry/idempotency/DLQ design • Azure Service Bus abstraction |

Integration / Daily flow: Verify local event flow and failure handling.

Day complete when: Messaging foundation passes.

# PHASE 5 — EXAM SERVICE

## Day 19 — Phase 5: Exam foundation

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create Admin Dashboard shell • Exam list placeholder | • Create Exam service projects • Exam entity • DbContext |

Integration / Daily flow: Frontend model prepared for Exam API.

Day complete when: Exam DB foundation works.

## Day 20 — Phase 5: Exam persistence

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create Create Exam form UI • Client-side validation | • Migration • Repository • CreateExam command/handler |

Integration / Daily flow: Form maps to CreateExam request.

Day complete when: CreateExam API works.

## Day 21 — Phase 5: Exam APIs

| Frontend — React | Backend — .NET |
| --- | --- |
| • Exam list/details pages • React Query hooks | • POST/GET/GET-by-id APIs • Validation • Tests • Gateway route |

Integration / Daily flow: Admin Exam UI consumes Gateway.

Day complete when: Admin can create/list/view exams.

## Day 22 — Phase 5: Exam UI completion

| Frontend — React | Backend — .NET |
| --- | --- |
| • Edit/view/publish UI foundation • Admin navigation | • Publish/unpublish rules • Authorization |

Integration / Daily flow: Admin workflow is complete.

Day complete when: Exam management end-to-end.

# PHASE 6 — QUESTION SERVICE

## Day 23 — Phase 6: Question foundation

| Frontend — React | Backend — .NET |
| --- | --- |
| • Question management page shell • Question form model | • Question/Option entities • Question service projects |

Integration / Daily flow: Frontend contract matches Question model.

Day complete when: Question DB foundation works.

## Day 24 — Phase 6: Question persistence

| Frontend — React | Backend — .NET |
| --- | --- |
| • Option editor UI • Correct-answer selection | • DbContext • Migrations • Repository • Relationships |

Integration / Daily flow: Question/Options payload validated.

Day complete when: Question persistence works.

## Day 25 — Phase 6: Question APIs

| Frontend — React | Backend — .NET |
| --- | --- |
| • Question list/edit/delete UI • React Query integration | • CRUD APIs • Exam question listing • Validation • Gateway route |

Integration / Daily flow: Admin can manage questions from React.

Day complete when: Question CRUD works end-to-end.

## Day 26 — Phase 6: Question UI gate

| Frontend — React | Backend — .NET |
| --- | --- |
| • Question preview • Exam/question navigation | • Tests • Authorization • Error handling |

Integration / Daily flow: Admin Exam → Questions flow complete.

Day complete when: Question Service gate passes.

# AI MILESTONE — AI QUESTION GENERATION

## Day 27 — AI Milestone: AI service foundation

| Frontend — React | Backend — .NET |
| --- | --- |
| • Create AI Question Generator page • Fields: Subject, Topic, Difficulty, Count, Type, Duration | • Create AI API/Application/Domain/Infrastructure • AI request/response contracts • Provider abstraction |

Integration / Daily flow: Frontend form is ready for POST /api/ai/questions/generate.

Day complete when: AI service builds and endpoint contract is ready.

## Day 28 — AI Milestone: AI generation

| Frontend — React | Backend — .NET |
| --- | --- |
| • Generate button • Loading/progress state • Error handling | • Build prompt • Call OpenAI/Azure OpenAI • Require structured JSON • Validate JSON/questions |

Integration / Daily flow: React → Gateway → AI Service → AI Provider.

Day complete when: Valid AI draft questions return to React.

## Day 29 — AI Milestone: AI review

| Frontend — React | Backend — .NET |
| --- | --- |
| • Review cards • Approve/Edit/Reject/Regenerate UI • Edit question/options | • Validate approval payload • Keep draft separate from Question DB • Add audit metadata model if needed |

Integration / Daily flow: AI drafts remain drafts until Admin approval.

Day complete when: Admin can review all generated questions.

## Day 30 — AI Milestone: AI approval integration

| Frontend — React | Backend — .NET |
| --- | --- |
| • Approved questions appear in Question Management UI • Success/error notifications | • Send approved questions to Question Service • Persist approved questions • Tests |

Integration / Daily flow: React → AI Service → Review → Question Service → Question DB.

Day complete when: Human approval gate works end-to-end.

# PHASE 7 — SUBMISSION / TAKE EXAM

## Day 31 — Phase 7: Submission foundation

| Frontend — React | Backend — .NET |
| --- | --- |
| • Student My Exams page • Exam details page | • Submission projects • ExamSubmission/SubmittedAnswer entities |

Integration / Daily flow: Student UI uses Exam API data.

Day complete when: Submission DB foundation works.

## Day 32 — Phase 7: Submission API

| Frontend — React | Backend — .NET |
| --- | --- |
| • Take Exam page • Question navigation • Answer state | • Start attempt • Save/submit answers • Validation • Submission event |

Integration / Daily flow: React submits answers to Submission API.

Day complete when: Submission succeeds.

## Day 33 — Phase 7: Submission gate

| Frontend — React | Backend — .NET |
| --- | --- |
| • Timer • Submit confirmation • Submission result state | • Duplicate submission protection • Tests • Event publication |

Integration / Daily flow: Complete Student → Submit flow.

Day complete when: Exam can be taken and submitted.

# PHASE 8 — RESULT SERVICE

## Day 34 — Phase 8: Result foundation

| Frontend — React | Backend — .NET |
| --- | --- |
| • Result page shell | • Result projects/entity/DbContext |

Integration / Daily flow: Prepare result contract.

Day complete when: Result DB foundation works.

## Day 35 — Phase 8: Result calculation

| Frontend — React | Backend — .NET |
| --- | --- |
| • Result loading state • Result summary UI | • Consume submission event • Calculate MCQ score deterministically • Persist Result • Publish ResultPublishedEvent |

Integration / Daily flow: Submission → Result.

Day complete when: Result generated automatically.

## Day 36 — Phase 8: Result UI

| Frontend — React | Backend — .NET |
| --- | --- |
| • Score/percentage • Correct/incorrect review • Admin result view | • Result APIs • Authorization • Tests |

Integration / Daily flow: React consumes Result API through Gateway.

Day complete when: Result flow complete.

# PHASE 9 — NOTIFICATION

## Day 37 — Phase 9: Notification foundation

| Frontend — React | Backend — .NET |
| --- | --- |
| • Notification/alert UI foundation if needed | • Notification Service • Consume UserRegisteredEvent/ResultPublishedEvent |

Integration / Daily flow: Events drive notifications.

Day complete when: Consumers work.

## Day 38 — Phase 9: Notification delivery

| Frontend — React | Backend — .NET |
| --- | --- |
| • Show notification status/history if included in UI scope | • Email provider abstraction • Retry/error handling • Test delivery |

Integration / Daily flow: Event → Notification Service → delivery.

Day complete when: Notification flow works.

# PHASE 10 — DOCKER + AZURE

## Day 39 — Phase 10: Docker images

| Frontend — React | Backend — .NET |
| --- | --- |
| • Production React build/container • Environment configuration | • Dockerfiles for Gateway and services • Health checks |

Integration / Daily flow: Both frontend and backend containerize.

Day complete when: Images build successfully.

## Day 40 — Phase 10: Docker Compose

| Frontend — React | Backend — .NET |
| --- | --- |
| • Run React container | • Run Gateway/services/SQL Server/RabbitMQ • Compose networking • Environment variables |

Integration / Daily flow: React container → Gateway container → services.

Day complete when: Local container stack works.

## Day 41 — Phase 10: Azure deployment

| Frontend — React | Backend — .NET |
| --- | --- |
| • Production frontend configuration | • Azure SQL • Container hosting • Secrets/configuration • Networking |

Integration / Daily flow: React uses deployed Gateway URL.

Day complete when: Cloud services are reachable.

## Day 42 — Phase 10: CI/CD + final gate

| Frontend — React | Backend — .NET |
| --- | --- |
| • Frontend CI build/test | • Backend CI build/test • Container publish/deploy • Logs/monitoring |

Integration / Daily flow: Full system smoke test.

Day complete when: Frontend + backend + AI + messaging + DB deployment passes.

# Daily Completion Template

| Check | Frontend | Backend |
| --- | --- | --- |
| Code completed | ☐ | ☐ |
| Build successful | ☐ | ☐ |
| Tests successful | ☐ | ☐ |
| API/UI integration verified | ☐ | ☐ |
| Errors resolved | ☐ | ☐ |
| Git commit created | ☐ | ☐ |

# Current Starting Point

DAY 1 — PHASE 0 — REPOSITORY + TOOLING SETUP

Today we work on both sides: create the React frontend structure AND create the .NET backend solution structure. The day is complete only when both sides build/run and the folder separation is correct.

# Final Rule

Every day = Frontend + Backend + Integration + Verification.